## Introduction
How to use: Review each stage Go through each tab and assess whether the organisation has considered the listed items. These include: Communication strategies Equality, Diversity & Inclusion (EDI) considerations Resident support mechanisms Feedback and monitoring processes Tick “Yes” or “No” based on whether the organisation has addressed each item. Add notes where relevant Use the notes column to: Highlight strengths or gaps Record feedback Note any follow-up actions or questions 🔹 Not every cell needs to be filled—only add notes where there is something to comment on. Refer to the resident engagement toolkit For deeper understanding or clarification, refer to the Resident Engagement Toolkit, which complements this checklist and provides detailed guidance on each stage. Tips for effective use Use this tool during project reviews, planning sessions, or funding assessments. Collaborate with colleagues to ensure a comprehensive review. Keep the checklist updated as the project progresses or new insights emerge.
Contents
Project Plan
Tasks
Task Tracker
Retrofit Resident Engagement Action Plan
The purpose of this Action Plan is to assist you with mapping out and planning your resident engagement approach for retrofit. It provides practical steps you can take to help put people first and reduce risks in your project delivery, as well as lessons learned from previous retrofit projects and recommended online resources. There are core milestones and KPIs pre-populated to help guide your resident engagement however PAs can update as appropriate to their resident engagement approach.
The Tasks and Task Tracker tab may be used to monitor and record progress against key activities and milestones. These tabs should be updated so that they reflect the sub-tasks required to complete the main activities identified in your project plan.
Funded by

## Project Plan
Resident Engagement Project Plan
| Name(s) | Project start: | 2025-10-01
Project Lead: |  | Todays date: | 2025-11-25
Resident engagement team: |  | Display week | 0
[8 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27
 | time axis 2025-09-22 to 2025-11-02
Resident engagement plan stage | CORE MILESTONE/ KPIs | OWNER | NOTES | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Engagement and consultation | Review and document resident engagement lessons learned from previous retrofit programmes
Development of resident engagement and marketing plans
Identification of key contacts including dedicated internal resident liaison support
Consult local residents for feeedback on plans. Establish feedback loop for continuous improvement
Establish a monitoring and evaluation plan
Awareness | Analysis of resident data to determine key characteristics and potential barriers to engagement
Identification of communication needs & preferences including additional support for vulnerable residents (e.g., neurodiversity, older people etc.)
Training staff to ensure their ability to engage and support EDI needs of residents
Identify and reach out to ‘key individuals’ who could support project and encourage resident signups
Launch | Develop and finalise launch strategy
Action launch strategy
Identify resident champions and case studies to support signups (ongoing)
Introduce residents to key staff, including contractor
Design | Process established to communicate and get feedback from residents about proposed retrofit designs
Review designs for accessibility and inclusiveness
Installation | Training, employment and community engagement opportunities identified
Communication and resident complaint management established (internal and external responsibilities identified)
Regular visits to ensure contractor is minimising disruption and supports in place for vulnerable residents
Handover | Tailored advice and guidance provided to residents
Handover session scheduled
Post-installation support and monitoring
Review all feedback and response, to feed into lessons learned

## Tasks
Resident Engagement Project Plan
| Name(s) | Project start:
Project Lead: |  | Todays date:
Resident engagement team:
TOPIC | CORE MILESTONE/ KPIs | OWNER | TASKS
Engagement planning | Strategic purpose of resident engagement |  | • Map the strategic purpose of resident engagement in your retrofit plan to: o Organisational strategic policies and regulatory drivers o Draw up a list of the benefits of resident engagement for your organisation o Create a resident engagement action plan with timescales and budget costs o Consider the benefits of a consortium project for delivery of resident engagement o Consider if staff resources should be in-house or contracted out o Liaise with other teams, including resident groups, to help plan your resident engagement
Benefits of resident engagement for organisation
Costs and financing resident engagement
Resources required for resident engagement
Define metrics for successful resident engagement
Awareness stage | Established how and what to communicate to residents |  | • How to communicate with residents: o Plan your communication methods o Train internal staff and contractors involved in the retrofit project o Make your residents feel special! o Ensure that all information materials are ‘resident friendly’ o Contact residents using the best ‘contact method’ in order of preference o Confirm with residents how they prefer to be contacted in the future o Have one single point of contact for residents o Select your resident engagement tools
• What to communicate to residents: o Plan your communications content o Include information on the residents’ typical concerns o Consider Whole House Approach during retrofit works o Create a short and simple ‘Retrofit project fact sheet’ summary document o Engage with residents based on their motivations o Get permission to install energy monitoring equipment in homes before retrofit works begin o Tailor communication methods and content for engaging with leaseholder tenants o Provide opportunities for residents to feedback or be involved
Launch stage | Full details of retrofit project are intrduced to residents, staff, and contractors |  | • Contact residents you have not heard from during the Awareness Stage • Use engaging and trusted staff to liaise with residents • Bring in the Retrofit Coordinator (RC) to support the engagement • Minimise engagement fatigue! • Contact more homes than required for retrofit project • Install monitoring equipment in homes before retrofit works begin • Consider all safeguarding and lone working requirements to protect residents • Get the residents interested through visual aids
Design stage | Provide tailored advice to residents about the retrofit measures to be installed |  | • Keep the residents up to date and as informed as they want to be • Consider the materials used to engage with residents • Ensure all retrofit advice according to PAS 2035 is provided to residents • Ensure that all planned measures are suitable for the residents
Installation stage | Maintain residents happiness during installation process |  | • Maintain strong project management • Offer regular updates for residents through bulletin boards and newsletters • Monitor residents’ satisfaction • Help residents to cope with the disruption • Keep a tidy working environment on site • Focus particularly on the hard-to-reach groups to ensure their concerns are responded to • Keep number of visits from contractors to a minimum.
Handover stage | Create in person tailored advice service for residents on the measures installed in their homes |  | • Provide tailored energy advice to residents according to PAS 2035 • Share post works energy performance metrics (such as EPC or SAP score) with residents • Provide resident friendly clear guidance on all new retrofit measures installed. Consider communication carefully - written guides may not always be best • Provide information to internal teams and repairs and maintenance contractors • Conduct an aftercare walkthrough, with reachback options (such as video or online tutorial reminders)
Provide tailored written guidence on how to use the fitted measures installed in residents homes.
Post-works stage | Post-occupancy monitoring and evaluation surveys |  | • Undertake post-occupancy evaluation surveys • Report on resident engagement outcomes and adapt methods of engagement for future retrofit plans • Undertake post-occupancy evaluation surveys • Introduce residents to maintenance teams • Repeat the retrofit information for residents in the different formats • Prepare for any future changes to tenants or contractors

## Task Tracker
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS
0%
Action number | Parent task | Name (s) | TASK PROGRESS | STATUS | COMMENTS
Action 1 | Engagement planning |  |  | Not Started | Begin Mid-April, finalsing end of April to beginning May.
Action 2 |  |  | 20% | In Progress
Action 3 | Awareness stage |  |  | Not Started
Action 4 |  |  | 100% | Completed |  | l
Action 5 |  |  |  | Not Started | Aim to begin at start of March.
Action 6 | Launch stage |  |  | Not Started | Aim to be finalised by end of March.
Action 7 |  |  | 50% | In Progress
Action 8 | Design stage |  |  | Not Started
Action 9 |  |  | 30% | In Progress | Aim to be finalised by end of May, begin amendments in April.
Action 10 | Installation stage |  |  | Not Started | Complete by end of 08/03/2024
Action 11 | Handover stage |  | 45% | In Progress | Begin week commencing 04 March.
Action 12 |  |  |  | Not Started | Start task at beginning of March.
Action 13 | Post-works stage |  |  | Not Started
Action 14 | Post-works stage |  |  | Not Started